## Master Plan
<Projec Team Members>
| 김광균 | Bruce KwangKyun Kim
| 조일규 | Ilgyu Cho
| 박호용 | Hoyong Park
| 임한동 | Handong Lim
| 한건희 | Kunhee Han
Year
[5 empty] | Month | 8 |  |  | 9 |  |  |  |  | 10 |  |  |  | 11 |  |  |  | 12
|  | Application |  |  | Week | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Project Formulation & Idea Generation (서비스 구상 및 프로젝트 구성)
Idea Geneartion (아이디어 정리)
Scenario (시나리오)
Function List (기능 리스트)
Project Team Build
App Planning (앱 기획)
Process Flow Chart (화면 플로우 차트)
Wireframe
Specific Function List
Development Reveiw (기술 검토 및 견적)
Server Use (서버 사용 여부 결정)
Server Architecture (서버 아키텍쳐 설계)
App Architecture (앱 아키텍쳐 설계)
Support Platform (Android, iOS) 지원 플랫폼 결정
Support API Version (지원 API 버전 결정)
Support Device (지원 디바이스 결정)
Project Schedule & Budget (프로젝트 기간 및 견적 도출)
App Design (앱 디자인)
Design Guide Review (디자인 가이드 검토)
Other App UX/UI Case Review (유사 앱 UX/UI 검토)
Theme (테마 선택)
Theme Customization (테마 커스텀 작업)
API Server Development
Interface Design (인터페이스 설계)
DB Design (DB 설계)
Development (Environment included) 개발 환경 셋팅 및 개발
App Development
App Test
Test Requirment (테스트 명세서 정리)
Integrated Test (통합 테스트)
Device Test (디바이스 테스트)
User Beta Test(사용자 베타 테스트)
|  |  | App Publish | Publish (배포용 앱 빌드)
Market Register (마켓 등록)
Marketing (마켓팅 활동)
Autonomous Parking
Parking Lot Perception
<Low Level Vision Algorithm>
data 전처리+algorithm |  |  | Parking Slot Detection | Algorithm
Data Set Preprocessing
RPI Implementation
Parking Avaliability Deep Learning
DCNN 'One-Stage' Algorithm
Model Compression
RPI Implementation
Parking Control
Proto Build
Path Planning & Optimization
Motion Plannning (Collision free, Leveling)
RPI Implementation
Validation
Environment Setting
Parking Test
Report Publish
Note on E11: ====== ID#AAAAHFC1jSw 김광균 (2020-10-10 02:28:32) Target Customers Customers Needs Values Object
Note on E14: ====== ID#AAAAHFC1jSs 김광균 (2020-10-10 02:28:32) Business Development 1) Software Planner, Designer, Frontend, Backend 2) Hardware Developer
Note on D16: ====== ID#AAAAHFC1jSo 김광균 (2020-10-10 02:28:32) 기획 > 디자인 > 개발 > 테스트 > 출시 Plan -> Design -> Development -> Test -> Implementation -> Operation
Note on D56: Canny Edge Hough Transform Ransac Radon Transform Harris Corner Detection Implemention (Rpi)
Note on E57: 1) tongji 2) parking slot detection

## SoftWareBacklog
HW/SW Interface | Features | Details | Priority | Assignee | Date
| Camera | OpenCV module | 1 |  | 11
|  | PiCamera module | 1 |  | 11
|  | pin setup | 1 |  | 11
|  | Modulize for object detection, parking lot detection | 1 |  | 11
|  | HW Testing | 1 |  | 11
| DC Motor | TB6612 Motor Driver | 1 |  | 11
|  | PWM setup | 1 |  | 11
|  | pin setup (4 pins) | 1 |  | 11
|  | HW Testing | 1 |  | 11
| Servo Motor | Camera Position Control | 1 |  | 11
|  | pin setup | 1 |  | 11
|  | PCA9685 Wheel Steering | 3 |  | 11
|  | HW Testing | 1 |  | 11
| Ultrasonic Sensor | pin setup | 1 |  | 11
|  | modulize | 1 |  | 11
|  | HW Testing | 1 |  | 11
| Car | Forward | 2 |  | 11
|  | Backward | 2 |  | 11
|  | Stop | 2 |  | 11
|  | Steering with DC motors | 2 |  | 11
|  | Steeting with Servo motors | 3 |  | 11
Algorithm | Lane Detection Low Level | HW Testing | 1
|  | Canny Edge,Hough Transform, RANSAC, radon, harris | 1
|  | Evaluation Metric |  |  | z
| Deep Learning | One-Stage Model Training | 1
Deploy with Light-Weight Model
Object Detection
Evaluation Metric
HW Testing
| Parking Mode Algorithm | Detect Parking Lot | 1
|  | Caculate min-radius and initial position | 1
|  | Move to initial position | 1
|  | Parking End Condition | 1
| Data Preprocessing | Tongji Data
wuzzh Data
| Environment | Test Case Setup

## Reference Links
Contents | Reference Link
autonomous parking | https://github.com/lymhust/awesome-parking-slot-detection
App Plan Perfect Guide | https://devcompass.co.kr/%EC%95%B1-%EC%A0%9C%EC%9E%91/#:~:text=%EC%A0%84%EB%B0%98%EC%A0%81%EC%9D%B8%20%EC%95%B1%20%EC%A0%9C%EC%9E%91%20%EB%8B%A8%EA%B3%84%EB%8A%94,%EC%9D%BC%EC%9D%84%20%EC%A7%84%ED%96%89%ED%95%A0%20%EC%88%98%20%EC%97%86%EC%8A%B5%EB%8B%88%EB%8B%A4.
Wire Frame | https://www.venturesquare.net/544639
https://blog.naver.com/PostView.nhn?blogId=durandot&logNo=221024396344&categoryNo=55&parentCategoryNo=-1&viewDate=&currentPage=&postListTopCurrentPage=&isAfterWrite=true

## DeepPiCar
DeepPi Car SW structure
Driving MODE | Requried Functions & Library | Sub-func | Input | Output | Contents | Requirements | Test
Perception & Work Plan | image_lane() | detection | camer img | lane frame | Lane detection and front wheel control | end-to-end model | O
|  | control | lane-frame | steering angle | Lane detection and front wheel control | end-to-end model
image_detection
|  | detection | camera img | objects:[{obj1:{bounding_box:[],...},...],frame | object detection | Need to Define Label
|  | contorl | objects
|  | resume_driving | changed_car_state |  | control according to car state
| object | is_close | frame | obj, frame_height, min_height_pct | Whether object is close | Need to Define types of objects
|  | set_car_state | current_car_state |  | Set Current State of the car
openCV
Steering & Motor control
| front_wheel | Left |  |  | Needs development
|  | Right |  |  | Needs development
calibration
| Back_wheel | forward
backward
calibration
| TB6612 | stop |  |  | Motor Class(GPIO channel,PWM channel setup)
| PCA9685 |  |  |  | pwm related module
| smbus |  |  |  | i2c module
Parking MODE
Perception & Work Plan | parking_area_detect | Not_occupied()
|  | lot_type() | parallel, rear-parking, front-parking,
| object_detection | parking_line_infringement
surrounding_object
is_able()
Steering & Motor control | path optimization